## Sheet1
Bug ID | Summary | Module | Description | Preconditions | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Environment | Defect Type | Attachment | Comments
BUG_001 | The user is unable to see the Photos inside the See all option in Home page. | Home Page | When the user opens the app and taps on the 'See all' text under the Gallery section, user gets the prompt 'No Results Found'. | User should have access to the Educase app. | 1. Open the Educase app. | All the photos from the Gallery should be displayed. | The user is redirected to another page which shows No Result Found. | High | Medium |  | Device: Android | Functional
|  |  |  | The Home page should be ready. | 2. Scroll down in the home page. | [5 empty] | OS : Android 16
|  |  |  | Internet connection should be active | 3. Locate the 'Gallery' section.
4. Tap on 'See all' link text.
5.Observe the behaviour of app.
BUG_002 | The user is unable to view the Latest News | Home Page | When the user open the app and taps on the Latest News under the Latest News section, user is being directed to another page which shows the source code of the page. | User should have access to the Educase app. | 1. Open the Educase app. | The Latest News page should be displayed and the latest news items should be displayed correctly. | The source code of the page displays instead of Latest News items inside the Latest News page. | High | Medium |  | Device: Android | Functional
|  |  |  | The Home page should be ready. | 2. Scroll down in the home page. | [5 empty] | OS : Android 16
|  |  |  | Internet connection should be active | 3. Locate the 'Latest News' section and tap it.
4. Analyse the latest news.
BUG_003 | The phone number is incorrect inside the Contact Module. | Contact Module | When the user open the app, taps on the Contact Module, the phone number in the 'Alternative Mobile Number' section is found incorrect. | User should have access to the Educase app. | 1. Open the Educase app. | The phone number must be of 10 digits. | The phone number is of 8 digits. | High | High |  | Device: Android | Functional
|  |  |  | Contact Us module should be ready and available. | 2. Tap on the Contact module. | [5 empty] | OS : Android 16
4. Verify the alternate number.
BUG_004 | The website link under the 'Social Links' section is unabe to redirect the user to the official website of Educase app. | Contact Module | When the user opens the app, taps on the Contact Module, the globe icon on under the 'Social Links' redirects to google search webpage. | User should have access to the Educase app. | 1. Open the Educase app. | The user should be redirected to the Educase app’s official website successfully. | The user is being redirected to google search webpage instead of their official website. | High | High |  | Device: Android | Functional
|  |  |  | Contact Us module should be available. | 2. Tap on the Contact module. | [5 empty] | OS : Android 16
|  |  |  | Internet connection should be active | 3. Tap on the globe icon.
|  |  |  | Any web browser should be installed and set as default on the mobile. | 4. Verify that the official site of the Educase app opens in the default web browser.
BUG_005 | The YouTube link under the 'Social Links' section is unabe to redirect the user to the official YouTube channel of Educase app. | Contact Module | When the user opens the app, navigates to Contact Module, the YouTube icon under the 'Social Links' redirects to google seach webpage. | User should have access to the Educase app. | 1. Open the Educase app. | The user should be directed to the official YouTube channel of the Educase app successfully. | The user is being redirected to google search webpage instead of their official YouTube channel. | High | Medium |  | Device: Android | Functional
|  |  |  | Contact Us module should be available. | 2. Tap on the Contact module. | [5 empty] | OS : Android 16
|  |  |  | Internet connection should be active | 3. Tap on the YouTube icon.
|  |  |  | Any web browser should be installed and set as default on the mobile. | 4. Verify that the official YouTube page of the Educase app opens in the default web browser.
BUG_006 | The Facebook link under the 'Social Links' section is unabe to redirect the user to the official Facebook page of Educase app. | Contact Module | When the user opens the app, navigates to Contact Module, the Facebook icon under the 'Social Links' redirects to google seach webpage. | User should have access to the Educase app. | 1. Open the Educase app. | The user should be directed to the official Facebook page of the Educase app successfully. | The user is being redirected to google search webpage instead of their official Facebook page. | High | High |  | Device: Android | Functional
|  |  |  | Contact Us module should be available. | 2. Tap on the Contact module. | [5 empty] | OS : Android 16
|  |  |  | Internet connection should be active | 3. Tap on the Facebook icon.
|  |  |  | Any web browser should be installed and set as default on the mobile. | 4. Verify that the official Facebook page of the Educase app opens in the default web browser.
BUG_007 | The Instagram link under the 'Social Links' section is unabe to redirect the user to the official Instagram page of Educase app. | Contact Module | When the user opens the app, navigates to Contact Module, the Instagram icon under the 'Social Links' redirects to google seach webpage. | User should have access to the Educase app. | 1. Open the Educase app. | The user should be directed to the official Instagram page of the Educase app successfully. | The user is being redirected to google search webpage instead of their official Instagram page. | High | High |  | Device: Android | Functional
|  |  |  | Contact Us module should be available. | 2. Tap on the Contact module. | [5 empty] | OS : Android 16
|  |  |  | Internet connection should be active | 3. Tap on the Instagram icon.
|  |  |  | Any web browser should be installed and set as default on the mobile. | 4. Verify that the official Instagram page of the Educase app opens in the default web browser.
BUG_008 | The Twitter link under the 'Social Links' section is unabe to redirect the user to the official Twitter page of Educase app. | Contact Module | When the user opens the app, navigates to Contact Module, the Twitter icon under the 'Social Links' redirects to google seach webpage. | User should have access to the Educase app. | 1. Open the Educase app. | The user should be directed to the official Twitter page of the Educase app successfully. | The user is being redirected to google search webpage instead of their official Twitter page. | High | High |  | Device: Android | Functional
|  |  |  | Contact Us module should be available. | 2. Tap on the Contact module. | [5 empty] | OS : Android 16
|  |  |  | Internet connection should be active | 3. Tap on the Twitter icon.
|  |  |  | Any web browser should be installed and set as default on the mobile. | 4. Verify that the official Twitter page of the Educase app opens in the default web browser.
BUG_009 | The LinkedIn link under the 'Social Links' section is unabe to redirect the user to the official LinkedIn page of Educase app. | Contact Module | When the user opens the app, navigates to Contact Module, the LinkedIn icon under the 'Social Links' redirects to google seach webpage. | User should have access to the Educase app. | 1. Open the Educase app. | The user should be directed to the official Linkedin page of the Educase app successfully. | The user is being redirected to google search webpage instead of their official LinkedIn page. | High | High |  | Device: Android | Functional
|  |  |  | Contact Us module should be available. | 2. Tap on the Contact module. | [5 empty] | OS : Android 16
|  |  |  | Internet connection should be active | 3. Tap on the LinkedIn icon.
|  |  |  | Any web browser should be installed and set as default on the mobile. | 4. Verify that the official LinkedIn page of the Educase app opens in the default web browser.